## Project Scope Statement
KELOMPOK 2 PROJECT SCOPE STATEMENT
PROJECT NO. | PROJECT NAME | DATE SUBMITTED
PROJECT/001 | GAME CHALLENGE & RESTAURANT CUSTOMER POINTS | 2021-03-24
PROJECT OBJECTIVES Describe the high-level goals of the project and how they relate to overall business objectives. | Membuat Aplikasi Game Challenge (Dino Run) yang dapat dimainkan berbasis WEB
Membuat Sistem Points untuk setiap pembelian oleh Pelanggan di Restoran (berhadiah potongan harga)
Step 1. Project Deliverables
Please list all project deliverables and briefly describe each. Do not list dates. Add more rows as necessary.
DELIVERABLE NO. | DESCRIPTION
1 | Project Plan
2 | Laporan
3
Step 2. List of Project Tasks
Please list all project tasks to be completed, based on the deliverables listed in the previous section. Do not list dates. Add more rows as necessary.
Alternatively, you can attach your work breakdown structure (WBS) to the scope statement. | Work Breakdown Structure (WBS) Link if applicable | WBS Attached?
YES [ ] ¦ NO [ ]
TASK NO. | DESCRIPTION | FOR DELIVERABLE NO. … ENTER TASK #
1 | Analisis
2 | Planning
3 | Eksekusi
4 | Login
5 | Login Form
6 | Login Remember me
7 | Login Forgot Password
8 | Sign Up
9 | Form Pendaftaran
10 | User
11 | Transaksi
12 | Game Challange
13 | Kategori
14 | Produk List
15 | Admin
16 | Master Transaksi
17 | Master User
18 | Master Kategori
19 | Master Produk
20 | Master Challange
21 | Master Level User
22 | Testing
23 | Maintenance
24 | Dokumentasi
25 | Closing Proyek
Step 3. Out of Scope
Please list the deliverables or tasks that you will not complete or provide as outputs of this project.
This project will NOT accomplish or include the following: | Network, Server, Hosting
Step 4. Project Assumptions
Please list any project factors that you consider to be true, real, or certain. Assumptions generally involve a certain degree of risk.
NO. | ASSUMPTION
1 | Time Management yang baik
2 | Koordinasi dan kerja tim
3 | Skills and capability
Step 5. Project Constraints
PROJECT START DATE | LAUNCH / GO-LIVE DATE | PROJECT END DATE
00/00/2021 | - | -
LIST ANY HARD DEADLINE(S)
LIST OTHER DATES / DESCRIPTIONS OF KEY MILESTONES
BUDGET CONSTRAINTS Enter information about project budget limitations (total project budget, maximum budget for key project deliverables). | 22300000
QUALITY OR PERFORMANCE CONSTRAINTS Enter any other requirements for the functionality, performance, or quality of the project. | Aplikasi tidak hang ketika digunakan, Tidak ada bug, program berjalan dengan baik
EQUIPMENT / PERSONNEL CONSTRAINTS Enter any constraints regarding equipment or people that will impact the project. | Laptop, Network, Server lokal
REGULATORY CONSTRAINTS Enter any legal, policy, or other regulatory constraints. | Menguasai Keahlian komptuasi dasar, dan paham penggunaan aplikasi yang dibuat oleh tim
Step 6. Updated Estimates
Estimate the hours required to complete the project. Enter total # of hours |  | 7jam x 88 hari = 616 Jam
Step 7. Approvals
DATE SUBMITTED FOR APPROVAL | STAKEHOLDER NAME, TITLE, AND ROLE | DATE APPROVAL RECEIVED
2021-03-24 | Mr. Ardiawan - Lecturer - Guide

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.